## WBS Dictionary
WBS工作包排序图
| 项目名 |  |  | 项目经理
| AI未来教育 |  |  | 赵健羽
任务ID | 任务描述 | 依赖 | 负责人 | 项目资源 | 开始日期 | 预计完成日期 | 实际完成日期
1 | 项目策划以及初期制作 | 空 | 赵健羽 | 会议 | 2024-11-11 | 2024-11-15 | 2024-11-15
1.1 | UI图设计 | 1 | 阮佳奕 | 画图工具 | 2024-11-11 | 2024-11-15 | 2024-11-15
1.1.1 | 设计菜单界面 | 1.1 | 阮佳奕 | 画图工具 | 2024-11-11 | 2024-11-15 | 2024-11-15
1.1.2 | 和后端讨论交互需求 | 1.1 | 阮佳奕 | 会议 | 2024-11-11 | 2024-11-15 | 2024-11-15
1.2 | 完成前端第一个界面 | 1 | 周钜豪,李子晗 | VSCode | 2024-11-11 | 2024-11-15 | 2024-11-15
1.2.1 | 完成前端第一个界面 | 1.2 | 周钜豪,李子晗 | VSCode | 2024-11-11 | 2024-11-15 | 2024-11-15
1.2.2 | 与后端确定交互 | 1.2 | 周钜豪,李子晗 | VSCode | 2024-11-11 | 2024-11-15 | 2024-11-15
1.3 | 实现接口调用 | 1 | 罗嘉鹏,韩子源 | Pycharm | 2024-11-11 | 2024-11-15 | 2024-11-15
1.3.1 | 实现接口调用 | 1.3 | 罗嘉鹏,韩子源 | Pycharm | 2024-11-11 | 2024-11-15 | 2024-11-15
1.3.2 | 与前端对接数据处理 | 1.3 | 罗嘉鹏,韩子源 | Pycharm | 2024-11-11 | 2024-11-15 | 2024-11-15
1.4 | 知识库搭建 | 1 | 曹邵莹,胡悦 | Dify | 2024-11-11 | 2024-11-15 | 2024-11-15
1.4.1 | 搭建Dify知识库 | 1.4 | 曹邵莹,胡悦 | Dify | 2024-11-11 | 2024-11-15 | 2024-11-15
1.5 | 数据库搭建 | 1 | 赵健羽 | DataGrip | 2024-11-11 | 2024-11-15 | 2024-11-15
1.5.1 | 根据UI设计图初步设计数据库表 | 1.5 | 赵健羽 | DataGrip | 2024-11-11 | 2024-11-15 | 2024-11-15
1.5.2 | 绘制ER图 | 1.5 | 赵健羽 | DataGrip | 2024-11-11 | 2024-11-15 | 2024-11-15
1.5.3 | MySQL制表 | 1.5 | 赵健羽 | DataGrip | 2024-11-11 | 2024-11-15 | 2024-11-15
2 | 项目正式制作 | 1 | 赵健羽 | 会议 | 2024-11-18 | 2024-11-22 | 2024-11-22
2.1 | 全栈（前端+后端）开发 | 2 | 赵健羽 | Jetbrains | 2024-11-18 | 2024-11-22 | 2024-11-22
2.1.1 | 添加注册登录等功能 | 2.1 | 赵健羽 | Jetbrains | 2024-11-18 | 2024-11-22 | 2024-11-22
2.1.2 | 个人信息功能部署 | 2.1 | 赵健羽 | Jetbrains | 2024-11-18 | 2024-11-22 | 2024-11-22
2.1.3 | 添加密码加密解密功能 | 2.1 | 赵健羽 | Jetbrains | 2024-11-18 | 2024-11-22 | 2024-11-22
2.1.4 | 初步部署Java后台 | 2.1 | 赵健羽 | Jetbrains | 2024-11-18 | 2024-11-22 | 2024-11-22
2.1.5 | 前端登陆注册界面部署 | 2.1 | 赵健羽 | Jetbrains | 2024-11-18 | 2024-11-22 | 2024-11-22
2.1.6 | 添加前端Element-UI依赖 | 2.1 | 赵健羽 | Jetbrains | 2024-11-18 | 2024-11-22 | 2024-11-22
2.1.7 | 添加前端TS+ECharts | 2.1 | 赵健羽 | Jetbrains | 2024-11-18 | 2024-11-22 | 2024-11-22
2.1.8 | 添加邮箱验证码功能并部署 | 2.1 | 赵健羽 | Jetbrains | 2024-11-18 | 2024-11-22 | 2024-11-22
2.1.9 | 数据库查询功能 | 2.1 | 赵健羽 | Jetbrains | 2024-11-18 | 2024-11-22 | 2024-11-22
2.1.10 | Java方向Dify功能部署 | 2.1 | 赵健羽 | Jetbrains | 2024-11-18 | 2024-11-22 | 2024-11-22
2.1.11 | 实现初步数据库增删改查功能 | 2.1 | 赵健羽 | Jetbrains | 2024-11-18 | 2024-11-22 | 2024-11-22
2.1.12 | 修改数据库缺陷 | 2.1 | 赵健羽 | Jetbrains | 2024-11-18 | 2024-11-22 | 2024-11-22
2.1.13 | 后端动态验证邮箱是否存在以及合理,还有前端动态验证密码是否重复 | 2.1 | 赵健羽 | Jetbrains | 2024-11-18 | 2024-11-22 | 2024-11-22
2.1.14 | 后端输出树形课程-单元-章节的树形数据 | 2.1 | 赵健羽 | Jetbrains | 2024-11-18 | 2024-11-22 | 2024-11-22
2.1.15 | 学生选课后端操作 | 2.1 | 赵健羽 | Jetbrains | 2024-11-18 | 2024-11-22 | 2024-11-22
2.1.16 | 前端部署用户ID | 2.1 | 赵健羽 | Jetbrains | 2024-11-18 | 2024-11-22 | 2024-11-22
2.1.17 | 添加了Swagger文档 | 2.1 | 赵健羽 | Jetbrains | 2024-11-18 | 2024-11-22 | 2024-11-22
2.2 | 前端开发 | 2 | 周钜豪,李子晗,阮佳奕 | VSCode | 2024-11-18 | 2024-11-22 | 2024-11-22
2.2.1 | 完成第一个界面新的UI设计,完成第二个界面UI设计 | 2.2 | 周钜豪,李子晗,阮佳奕 | VSCode | 2024-11-18 | 2024-11-22 | 2024-11-22
2.2.2 | 跟后端对接,实现第一个界面对话框的前后端交互 | 2.2 | 周钜豪,李子晗,阮佳奕 | VSCode | 2024-11-18 | 2024-11-22 | 2024-11-22
2.2.3 | 学会Git链接并连接到代码仓库 | 2.2 | 周钜豪,李子晗,阮佳奕 | VSCode | 2024-11-18 | 2024-11-22 | 2024-11-22
2.2.4 | 继续写出第一个界面并进行美化 | 2.2 | 周钜豪,李子晗,阮佳奕 | VSCode | 2024-11-18 | 2024-11-22 | 2024-11-22
2.2.5 | 写出第二个界面（题库界面） | 2.2 | 周钜豪,李子晗,阮佳奕 | VSCode | 2024-11-18 | 2024-11-22 | 2024-11-22
2.3 | 后端开发 | 2 | 罗嘉鹏,韩子源 | Pycharm | 2024-11-18 | 2024-11-22 | 未完成
2.2.3 | 与AI方向对接,能读取出Dify工作流的同学的数据 | 2.3 | 罗嘉鹏,韩子源 | Pycharm | 2024-11-18 | 2024-11-22 | 未完成
2.2.4 | 把数据经过处理后,传到数据库和前端 | 2.3 | 罗嘉鹏,韩子源 | Pycharm | 2024-11-18 | 2024-11-22 | 2024-11-22
2.2.5 | 与前端方向对接,能实现题目显示功能 | 2.3 | 罗嘉鹏,韩子源 | Pycharm | 2024-11-18 | 2024-11-22 | 未完成
2.4 | Dify工作流完成 | 2 | 曹邵莹,胡悦 | Dify | 2024-11-18 | 2024-11-22 | 2024-11-22
2.4.1 | 与后端的对接,明白后端和前端都需要什么数据 | 2.4 | 曹邵莹,胡悦 | Dify | 2024-11-18 | 2024-11-22 | 2024-11-22
2.4.1 | 实现知识库出题功能 | 2.4 | 曹邵莹,胡悦 | Dify | 2024-11-18 | 2024-11-22 | 2024-11-22
2.4.1 | 最好能做个额外的AI讲题？ | 2.4 | 曹邵莹,胡悦 | Dify | 2024-11-18 | 2024-11-22 | 2024-11-22
3 | 完成第一阶段流程制作 | 2 | 赵健羽 | 会议 | 2024-11-25 | 2024-11-29 | 2024-11-29
3.1 | 全栈开发 | 3 | 赵健羽 | Jetbrains | 2024-11-25 | 2024-11-29 | 2024-11-29
3.1.1 | 添加内容自动生成 | 3.1 | 赵健羽 | Jetbrains | 2024-11-25 | 2024-11-29 | 2024-11-29
3.1.2 | 前端后端部署选课系统 | 3.1 | 赵健羽 | Jetbrains | 2024-11-25 | 2024-11-29 | 2024-11-29
3.1.3 | 增加前端树形表与后端对接以及数据解析 | 3.1 | 赵健羽 | Jetbrains | 2024-11-25 | 2024-11-29 | 2024-11-29
3.1.4 | 大改优化了前端界面 | 3.1 | 赵健羽 | Jetbrains | 2024-11-25 | 2024-11-29 | 2024-11-29
3.1.5 | AI出题 | 3.1 | 赵健羽 | Jetbrains | 2024-11-25 | 2024-11-29 | 2024-11-29
3.1.6 | AI写学习内容 | 3.1 | 赵健羽 | Jetbrains | 2024-11-25 | 2024-11-29 | 2024-11-29
3.1.7 | Swagger文档完善 | 3.1 | 赵健羽 | Jetbrains | 2024-11-25 | 2024-11-29 | 2024-11-29
3.1.8 | Redis优化加入 | 3.1 | 赵健羽 | Jetbrains | 2024-11-25 | 2024-11-29 | 2024-11-29
3.2 | 前端开发 | 3 | 周钜豪,李子晗,阮佳奕,曹邵莹,胡悦 | VSCode | 2024-11-25 | 2024-11-29 | 2024-11-29
3.2.1 | 完成题目的渲染 | 3.2 | 周钜豪,李子晗,阮佳奕,曹邵莹,胡悦 | VSCode | 2024-11-25 | 2024-11-29 | 2024-11-29
3.2.2 | 完成学习内容的前后端交互，测验的前后端交互 | 3.2 | 周钜豪,李子晗,阮佳奕,曹邵莹,胡悦 | VSCode | 2024-11-25 | 2024-11-29 | 2024-11-29
3.2.3 | 完成前端判题 | 3.2 | 周钜豪,李子晗,阮佳奕,曹邵莹,胡悦 | VSCode | 2024-11-25 | 2024-11-29 | 2024-11-29
3.2.4 | 继续优化一下界面 | 3.2 | 周钜豪,李子晗,阮佳奕,曹邵莹,胡悦 | VSCode | 2024-11-25 | 2024-11-29 | 2024-11-29
3.2.5 | Markdown渲染 | 3.2 | 周钜豪,李子晗,阮佳奕,曹邵莹,胡悦 | VSCode | 2024-11-25 | 2024-11-29 | 2024-11-29
3.2.6 | 配置好后端并且能运行 | 3.2 | 周钜豪,李子晗,阮佳奕,曹邵莹,胡悦 | VSCode | 2024-11-25 | 2024-11-29 | 2024-11-29
3.2.7 | 学习前后端fetch交互 | 3.2 | 周钜豪,李子晗,阮佳奕,曹邵莹,胡悦 | VSCode | 2024-11-25 | 2024-11-29 | 2024-11-29
3.3 | Python后端 | 3 | 罗嘉鹏,韩子源 | Pycharm | 2024-11-25 | 2024-11-29 | 2024-11-29
3.3.1 | 对数据库合理增加部分字段 | 3.3 | 罗嘉鹏,韩子源 | Pycharm | 2024-11-25 | 2024-11-29 | 2024-11-29
3.3.1 | 实现用户ID查询任务点完成情况等 | 3.3 | 罗嘉鹏,韩子源 | Pycharm | 2024-11-25 | 2024-11-29 | 2024-11-29
3.3.1 | 包装成后端接口并传给前端 | 3.3 | 罗嘉鹏,韩子源 | Pycharm | 2024-11-25 | 2024-11-29 | 2024-11-29
3.4 | AI | 3 | 曹邵莹,胡悦 | Dify | 2024-11-25 | 2024-11-29 | 2024-11-29
3.4.1 | 完成Dify工作流——出题 | 3.4 | 曹邵莹,胡悦 | Dify | 2024-11-25 | 2024-11-29 | 2024-11-29

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.